## Sheet1
Task | Start Day | End Day | Duration (Days)
Documentation | 0 | 42 | 42
Create A User Manual | 35 | 42 | 7
Improving | 35 | 42 | 7
Getting Feedback | 28 | 35 | 7
Testing/Debugging | 28 | 35 | 7
Graphics | 14 | 28 | 14
Physics Engine | 14 | 28 | 14
User Movement | 7 | 14 | 7
Learning Java3D API | 0 | 14 | 14
UML Class Diagram | 0 | 3 | 3
Scope Plan | 0 | 3 | 3