## Sheet1
Task | Start | Duration
Scope Plan | 0 | 2
Figuring out the needed Classes | 2 | 1
Deciding on the layout | 2 | 1
Graphics(Checker board and pieces) | 2 | 2
Mouse Listeners(checker pieces) | 4 | 3
Cases(Kings and elimination of pieces) | 7 | 7
Timer and Scoreboard | 13 | 1
Testing/Debugging | 14 | 2
Getting Feedbacks | 14 | 2
Improving | 16 | 3
Creating a user manual | 17 | 1
Documenting | 0 | 21